## List of Ecosystems
DO WORK |  |  |  |  | Do not Delete
List of Ecosystems | Current Time % |  | Future Time %
Each Row hyperlinks to the apropriate tab. Renaming the cell will only rename the go to worksheet and not the tab. You will need to rename the tab. | Person 1 | Person 2 | Person 1 | Person 2 | Ineffective
Masterplanning | 0% | 0% | 0% | 0% | Effective
Preconstruction | 0% | 0% | 0% | 0% | Efficient
Owner Contracts | 0% | 0% | 0% | 0% | Exceptional
Project Setup | 0% | 0% | 0% | 0%
Safety/ICRA/ILSM | 0% | 0% | 0% | 0%
Schedule Management | 0% | 0% | 0% | 0% | N/A
Relationship Management | 0% | 0% | 0% | 0% | Event based
Cost Management | 0% | 0% | 0% | 0% | Time based
Construction | 0% | 0% | 0% | 0% | Hourly
Project Closeout | 0% | 0% | 0% | 0% | Daily
The "Company" Way | 0% | 0% | 0% | 0% | Weekly
Risk Mangement | 0% | 0% | 0% | 0% | Bi Weekly
| 0% | 0% | 0% | 0% | Monthly
Quarterly
Annually
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Select the appropriate cell to go to that Ecosystem tab.

## Masterplanning
Masterplanning | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Strategy/Set up for success
Review/Update Discovery/DOS approach | [7 empty] | 0% | 0% | 0% | 0%
Assemble Internal Team | [7 empty] | 0% | 0% | 0% | 0%
Assemble External Team | [7 empty] | 0% | 0% | 0% | 0%
Roles/Responsibilities | [7 empty] | 0% | 0% | 0% | 0%
Alignment on Deliverables | [7 empty] | 0% | 0% | 0% | 0%
Alignment on Schedule | [7 empty] | 0% | 0% | 0% | 0%
Process
Establish Priorities/Drivers | [7 empty] | 0% | 0% | 0% | 0%
Facility Assessment | [7 empty] | 0% | 0% | 0% | 0%
Cost Model | [7 empty] | 0% | 0% | 0% | 0%
Schedule/Phasing | [7 empty] | 0% | 0% | 0% | 0%
Deliverable Development | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Preconstruction
Preconstruction | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Intangibles | [7 empty] | 0% | 0% | 0% | 0%
Design Partner Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Client Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Sub/Vendor Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Ownership of the Precon Process/Build Trust | [7 empty] | 0% | 0% | 0% | 0%
Delivery of Information | [7 empty] | 0% | 0% | 0% | 0%
Follow Pathway | [7 empty] | 0% | 0% | 0% | 0%
Conceptual
Scoping | [7 empty] | 0% | 0% | 0% | 0%
Phasing | [7 empty] | 0% | 0% | 0% | 0%
Scheduling | [7 empty] | 0% | 0% | 0% | 0%
Cost Modeling | [7 empty] | 0% | 0% | 0% | 0%
Smart Choices | [7 empty] | 0% | 0% | 0% | 0%
Estimate Review/Margin Maximization | [7 empty] | 0% | 0% | 0% | 0%
Alignment of Team | [7 empty] | 0% | 0% | 0% | 0%
Communication of Deliverable | [7 empty] | 0% | 0% | 0% | 0%
SD/DD/CD
Scoping Document | [7 empty] | 0% | 0% | 0% | 0%
Phasing | [7 empty] | 0% | 0% | 0% | 0%
Scheduling | [7 empty] | 0% | 0% | 0% | 0%
Cost Modeling | [7 empty] | 0% | 0% | 0% | 0%
Smart Choices | [7 empty] | 0% | 0% | 0% | 0%
Estimate Review/Margin Maximization | [7 empty] | 0% | 0% | 0% | 0%
Alignment of Team | [7 empty] | 0% | 0% | 0% | 0%
Envelope Review | [7 empty] | 0% | 0% | 0% | 0%
Testing/Commisioning Procurement | [7 empty] | 0% | 0% | 0% | 0%
Front end Specs | [7 empty] | 0% | 0% | 0% | 0%
Bid Scopes | [7 empty] | 0% | 0% | 0% | 0%
Constructability Review | [7 empty] | 0% | 0% | 0% | 0%
Site Logistics | [7 empty] | 0% | 0% | 0% | 0%
ICRA/ISLM Planning | [7 empty] | 0% | 0% | 0% | 0%
Cardboard Mockups | [7 empty] | 0% | 0% | 0% | 0%
Buyout
Procurement Planning | [7 empty] | 0% | 0% | 0% | 0%
Bid List Development | [7 empty] | 0% | 0% | 0% | 0%
Advertising Bids | [7 empty] | 0% | 0% | 0% | 0%
Recieving of Bids | [7 empty] | 0% | 0% | 0% | 0%
Bid Leveling | [7 empty] | 0% | 0% | 0% | 0%
Post Bid Interviews | [7 empty] | 0% | 0% | 0% | 0%
GMP Deliverable Creation | [7 empty] | 0% | 0% | 0% | 0%
Internal Review of GMP/Margin Maximization | [7 empty] | 0% | 0% | 0% | 0%
GMP Presentation/Communication | [7 empty] | 0% | 0% | 0% | 0%
Prepare Subcontracts w/ exhibits | [7 empty] | 0% | 0% | 0% | 0%
Review Subcontracts | [7 empty] | 0% | 0% | 0% | 0%
Send out for Signature | [7 empty] | 0% | 0% | 0% | 0%
Save in Project Folder | [7 empty] | 0% | 0% | 0% | 0%
Tax Exempt Certificates | [7 empty] | 0% | 0% | 0% | 0%
Sub Bonds | [7 empty] | 0% | 0% | 0% | 0%
CIO's | [7 empty] | 0% | 0% | 0% | 0%
W9's | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Owner Contracts
Owner Contracts | [11 empty] | Back to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Base Contract
Determine Type of Contract | [7 empty] | 0% | 0% | 0% | 0%
Use Project Startup Sheet | [7 empty] | 0% | 0% | 0% | 0%
Use of Templates | [7 empty] | 0% | 0% | 0% | 0%
Draft | [7 empty] | 0% | 0% | 0% | 0%
Negotiation of Terms | [7 empty] | 0% | 0% | 0% | 0%
Finalization of Contract | [7 empty] | 0% | 0% | 0% | 0%
Review w/Owner | [7 empty] | 0% | 0% | 0% | 0%
Signatures | [7 empty] | 0% | 0% | 0% | 0%
Save to Project Folder | [7 empty] | 0% | 0% | 0% | 0%
Amendment
Use of Templates | [7 empty] | 0% | 0% | 0% | 0%
Draft | [7 empty] | 0% | 0% | 0% | 0%
Assembly of Exhibits | [7 empty] | 0% | 0% | 0% | 0%
Review w/Owner | [7 empty] | 0% | 0% | 0% | 0%
Signatures | [7 empty] | 0% | 0% | 0% | 0%
Save to Project Folder | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Project Setup
Project Setup | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Startup
R& R Matrix | [7 empty] | 0% | 0% | 0% | 0%
Procore Setup | [7 empty] | 0% | 0% | 0% | 0%
Precon Handoff Mtg | [7 empty] | 0% | 0% | 0% | 0%
Permits | [7 empty] | 0% | 0% | 0% | 0%
Meeting Calendar Establishes | [7 empty] | 0% | 0% | 0% | 0%
Finalize Staffing Plan (Who) | [7 empty] | 0% | 0% | 0% | 0%
Meeting Agendas Established | [7 empty] | 0% | 0% | 0% | 0%
Marketing Opprotunities | [7 empty] | 0% | 0% | 0% | 0%
Establish Main Point of Contact | [7 empty] | 0% | 0% | 0% | 0%
Site Logistics
Marketing Opprotunities | [7 empty] | 0% | 0% | 0% | 0%
Utility Setup | [7 empty] | 0% | 0% | 0% | 0%
Surveying/Staking | [7 empty] | 0% | 0% | 0% | 0%
Trailer/Connex Mobilization | [7 empty] | 0% | 0% | 0% | 0%
Laydown Areas | [7 empty] | 0% | 0% | 0% | 0%
Fencing/Screening | [7 empty] | 0% | 0% | 0% | 0%
Existing Conditions Documentation | [7 empty] | 0% | 0% | 0% | 0%
Site Specific Safety Plan | [7 empty] | 0% | 0% | 0% | 0%
Information Board Steup | [7 empty] | 0% | 0% | 0% | 0%
Air Quality/Pre-Balance/Hazardous Materials Testing | [7 empty] | 0% | 0% | 0% | 0%
Financial
Format Estimate to Import | [7 empty] | 0% | 0% | 0% | 0%
Procore Import | [7 empty] | 0% | 0% | 0% | 0%
Establish Schedule of Values | [7 empty] | 0% | 0% | 0% | 0%
Setup Labor Margin Calculator | [7 empty] | 0% | 0% | 0% | 0%
Procurement
Creation and Execution | [7 empty] | 0% | 0% | 0% | 0%
Contracts Complete by 90 days | [7 empty] | 0% | 0% | 0% | 0%
Field
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Safety
Safety | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Company Safety Program | [7 empty] | 0% | 0% | 0% | 0%
Create/maintain safety manual | [7 empty] | 0% | 0% | 0% | 0%
Communicate / train changes annually | [7 empty] | 0% | 0% | 0% | 0%
Create/maintain Crisis Plan | [7 empty] | 0% | 0% | 0% | 0%
Communicate / train CP changes annually | [7 empty] | 0% | 0% | 0% | 0%
Create / Maintain Vehicle / Driver Safety Program | [7 empty] | 0% | 0% | 0% | 0%
Communicate / train VDS changes annually | [7 empty] | 0% | 0% | 0% | 0%
Site Specific Program
Create Site Specific Program for each project | [7 empty] | 0% | 0% | 0% | 0%
Communicate | [7 empty] | 0% | 0% | 0% | 0%
Jobsite safety orientation | [7 empty] | 0% | 0% | 0% | 0%
Third Party Consultants | [7 empty] | 0% | 0% | 0% | 0%
Accountability / Enforcement | [7 empty] | 0% | 0% | 0% | 0%
ICRA / ILSM
Create plan | [7 empty] | 0% | 0% | 0% | 0%
Communicate plan | [7 empty] | 0% | 0% | 0% | 0%
Update / maintain plan | [7 empty] | 0% | 0% | 0% | 0%
Implement environment controls | [7 empty] | 0% | 0% | 0% | 0%
Update / maintain environment controls | [7 empty] | 0% | 0% | 0% | 0%
Record Keeping Negative Air & Particulate | [7 empty] | 0% | 0% | 0% | 0%
Training / Equipment / PPE
Identify / Require training | [7 empty] | 0% | 0% | 0% | 0%
Train / record keeping | [7 empty] | 0% | 0% | 0% | 0%
PPE Availability | [7 empty] | 0% | 0% | 0% | 0%
Equipment Availability | [7 empty] | 0% | 0% | 0% | 0%
Maintenance training for equipment | [7 empty] | 0% | 0% | 0% | 0%
Safety Committee
Select representation / members | [7 empty] | 0% | 0% | 0% | 0%
Create / maintain safety standards | [7 empty] | 0% | 0% | 0% | 0%
Commuincate / implement / train safety standards | [7 empty] | 0% | 0% | 0% | 0%
Identify safety needs of company | [7 empty] | 0% | 0% | 0% | 0%
Create / Promote safety driven culture | [7 empty] | 0% | 0% | 0% | 0%
Communication & Reporting Incidents
Internal Reporting | [7 empty] | 0% | 0% | 0% | 0%
External Reporting | [7 empty] | 0% | 0% | 0% | 0%
OSHA Reporting | [7 empty] | 0% | 0% | 0% | 0%
Client Communicating | [7 empty] | 0% | 0% | 0% | 0%
Recognition
Create program | [7 empty] | 0% | 0% | 0% | 0%
Implement / maintain program | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Schedule Management
Schedule Management | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
CPM Schedule Updates
Initial Schedule Creation | [7 empty] | 0% | 0% | 0% | 0%
Phasing Planning | [7 empty] | 0% | 0% | 0% | 0%
Internal Team Buy-In | [7 empty] | 0% | 0% | 0% | 0%
External team buy-in | [7 empty] | 0% | 0% | 0% | 0%
Update Schedule | [7 empty] | 0% | 0% | 0% | 0%
Communicate Schedule | [7 empty] | 0% | 0% | 0% | 0%
Schedule Standards: Format / Logic | [7 empty] | 0% | 0% | 0% | 0%
Identifying Schedule Impacts | [7 empty] | 0% | 0% | 0% | 0%
Schedule Accountability | [7 empty] | 0% | 0% | 0% | 0%
Training | [7 empty] | 0% | 0% | 0% | 0%
6-Week Look Aheads
Create 6 Week Look Ahead | [7 empty] | 0% | 0% | 0% | 0%
Communicate / Hold Accountable | [7 empty] | 0% | 0% | 0% | 0%
Distribute | [7 empty] | 0% | 0% | 0% | 0%
Update Weekly | [7 empty] | 0% | 0% | 0% | 0%
Training | [7 empty] | 0% | 0% | 0% | 0%
Lean principles
Pull Plan - Lean Schedule Tool | [7 empty] | 0% | 0% | 0% | 0%
Update Procurement logs | [7 empty] | 0% | 0% | 0% | 0%
Daily Work Plans | [7 empty] | 0% | 0% | 0% | 0%
Daily Stand Ups | [7 empty] | 0% | 0% | 0% | 0%
Training | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Relationship Management
Relationship Management | [11 empty] | Cli
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Clients | [7 empty] | 0% | 0% | 0% | 0%
Weekly Project Updates | [7 empty] | 0% | 0% | 0% | 0%
Client Communication Tool | [7 empty] | 0% | 0% | 0% | 0%
OAC Meetings | [7 empty] | 0% | 0% | 0% | 0%
Weekly Hard Hat Tour | [7 empty] | 0% | 0% | 0% | 0%
Murray Sponsored Events | [7 empty] | 0% | 0% | 0% | 0%
One on one client contacts | [7 empty] | 0% | 0% | 0% | 0%
Keep Client Most Informed Person in the Room | [7 empty] | 0% | 0% | 0% | 0%
Crucial Conversations | [7 empty] | 0% | 0% | 0% | 0%
Design Partners
Gain Alignment before owner meetings | [7 empty] | 0% | 0% | 0% | 0%
No blindsides - meeting before the meeting | [7 empty] | 0% | 0% | 0% | 0%
Weekly Project Updates | [7 empty] | 0% | 0% | 0% | 0%
Client Communication Tool | [7 empty] | 0% | 0% | 0% | 0%
OAC Meetings | [7 empty] | 0% | 0% | 0% | 0%
Crucial Conversations | [7 empty] | 0% | 0% | 0% | 0%
Agreement on how we treat each other | [7 empty] | 0% | 0% | 0% | 0%
Trade Partners
Kickoff meetings | [7 empty] | 0% | 0% | 0% | 0%
Postbid Interviews | [7 empty] | 0% | 0% | 0% | 0%
Weekly trade partner meetings | [7 empty] | 0% | 0% | 0% | 0%
Pull plans / collective IQ meetings | [7 empty] | 0% | 0% | 0% | 0%
Trade Partner check ins - Random | [7 empty] | 0% | 0% | 0% | 0%
Lead sharing | [7 empty] | 0% | 0% | 0% | 0%
Appreciation / Celebration | [7 empty] | 0% | 0% | 0% | 0%
AHJ / Municipalities
Prejob conference | [7 empty] | 0% | 0% | 0% | 0%
Preinspections | [7 empty] | 0% | 0% | 0% | 0%
Understanding expectations | [7 empty] | 0% | 0% | 0% | 0%
Gratitude / Appreciation | [7 empty] | 0% | 0% | 0% | 0%
Internal
Mentoring - formal / informal | [7 empty] | 0% | 0% | 0% | 0%
Weekly Checkins | [7 empty] | 0% | 0% | 0% | 0%
Team Department meetings | [7 empty] | 0% | 0% | 0% | 0%
Staff Meetings - monthly | [7 empty] | 0% | 0% | 0% | 0%
Email Celebrations | [7 empty] | 0% | 0% | 0% | 0%
Pathway Committee | [7 empty] | 0% | 0% | 0% | 0%
Creating Opportunities for Leadership | [7 empty] | 0% | 0% | 0% | 0%
Company Events | [7 empty] | 0% | 0% | 0% | 0%
Sponsored Meals / Gatherings | [7 empty] | 0% | 0% | 0% | 0%
Personal Life Celebrations | [7 empty] | 0% | 0% | 0% | 0%
Performance Management | [7 empty] | 0% | 0% | 0% | 0%
Community
Knock and Talks | [7 empty] | 0% | 0% | 0% | 0%
Building Trades School Tours | [7 empty] | 0% | 0% | 0% | 0%
Community Project Tours | [7 empty] | 0% | 0% | 0% | 0%
Community Internship | [7 empty] | 0% | 0% | 0% | 0%
Sponsor Events | [7 empty] | 0% | 0% | 0% | 0%
Community Board Meetings / Presentation | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Cost Management
Cost Management | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Project Setup | [7 empty] | 0% | 0% | 0% | 0%
Final Estimate Review | [7 empty] | 0% | 0% | 0% | 0%
ProCore Import | [7 empty] | 0% | 0% | 0% | 0%
Initial Labor Margin Setup | [7 empty] | 0% | 0% | 0% | 0%
Initial Projection Setup | [7 empty] | 0% | 0% | 0% | 0%
Contingency and Allowance Setup | [7 empty] | 0% | 0% | 0% | 0%
Setup Reclassified Billing | [7 empty] | 0% | 0% | 0% | 0%
Monthly Cost Management
Cost to Complete/Monthly Projections | [7 empty] | 0% | 0% | 0% | 0%
Contingency Management | [7 empty] | 0% | 0% | 0% | 0%
Labor Margin/Hours Updates/Maximization | [7 empty] | 0% | 0% | 0% | 0%
Reclassified Equipment/Technology | [7 empty] | 0% | 0% | 0% | 0%
Change Order Process | [7 empty] | 0% | 0% | 0% | 0%
Allowance Managment | [7 empty] | 0% | 0% | 0% | 0%
Contingency /Change Log | [7 empty] | 0% | 0% | 0% | 0%
Billings/Invoicing | [7 empty] | 0% | 0% | 0% | 0%
T&M Ticket Tracking | [7 empty] | 0% | 0% | 0% | 0%
Close Out Cost Management
Retainage Billing | [7 empty] | 0% | 0% | 0% | 0%
Zero Dollar Change Orders to Subs | [7 empty] | 0% | 0% | 0% | 0%
Final Lien Waivers | [7 empty] | 0% | 0% | 0% | 0%
Final Change Order to Owner | [7 empty] | 0% | 0% | 0% | 0%
Warranty Accrual | [7 empty] | 0% | 0% | 0% | 0%
Final Pay Balance Reporting | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Construction
Construction | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Intangibles
Design Partner Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Client Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Sub/Vendor Relationship Building | [7 empty] | 0% | 0% | 0% | 0%
Ownership of the Precon Process/Build Trust | [7 empty] | 0% | 0% | 0% | 0%
Delivery of Information | [7 empty] | 0% | 0% | 0% | 0%
Project Documents
Produce / Maintain Project Procurement Log | [7 empty] | 0% | 0% | 0% | 0%
RFIs | [7 empty] | 0% | 0% | 0% | 0%
ASIs / PRs | [7 empty] | 0% | 0% | 0% | 0%
Processing Substitution Requests | [7 empty] | 0% | 0% | 0% | 0%
Processing Submittals | [7 empty] | 0% | 0% | 0% | 0%
Create / maintain submittal log | [7 empty] | 0% | 0% | 0% | 0%
Maintain live documents | [7 empty] | 0% | 0% | 0% | 0%
Daily Photos | [7 empty] | 0% | 0% | 0% | 0%
Daily Report | [7 empty] | 0% | 0% | 0% | 0%
Review & Analize Testing Reports | [7 empty] | 0% | 0% | 0% | 0%
Filing Testing Reports | [7 empty] | 0% | 0% | 0% | 0%
AHJ Inspections & Reports | [7 empty] | 0% | 0% | 0% | 0%
In project logistics planning | [7 empty] | 0% | 0% | 0% | 0%
Owner Furnished Equipment Install | [7 empty] | 0% | 0% | 0% | 0%
Low Voltage Matrix Coordination | [7 empty] | 0% | 0% | 0% | 0%
Preparing for Successful Punchlist | [7 empty] | 0% | 0% | 0% | 0%
Punchlist - Murray | [7 empty] | 0% | 0% | 0% | 0%
Punchlist - Design / Owner | [7 empty] | 0% | 0% | 0% | 0%
Quality Control
Preinstallation meeting | [7 empty] | 0% | 0% | 0% | 0%
Third Party Testing | [7 empty] | 0% | 0% | 0% | 0%
Survey Staking | [7 empty] | 0% | 0% | 0% | 0%
Third Party Indoor Air Quality Testing | [7 empty] | 0% | 0% | 0% | 0%
Daily Walk / Inspect / Correct | [7 empty] | 0% | 0% | 0% | 0%
Communication - Info Management
Team Communication Tool | [7 empty] | 0% | 0% | 0% | 0%
Weekly Project Update | [7 empty] | 0% | 0% | 0% | 0%
Internal Meetings
Project Kickoff | [7 empty] | 0% | 0% | 0% | 0%
JL10 | [7 empty] | 0% | 0% | 0% | 0%
R&R | [7 empty] | 0% | 0% | 0% | 0%
External Meetings
Trade Partner Coordination Meetings | [7 empty] | 0% | 0% | 0% | 0%
OAC | [7 empty] | 0% | 0% | 0% | 0%
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Project Closeout
Project Closeout | [11 empty] | Return to List of Ecosystems
Workflows | Frequency | Components Efficacy |  |  | Today's Workflow Efficacy | Future Workflow Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
|  | People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Project Documents | [7 empty] | 0% | 0% | 0%
Finalize and submit As-builts Drawings | [7 empty] | 0% | 0% | 0% | 0%
Create and submit closeout manual | [7 empty] | 0% | 0% | 0% | 0%
Conduct Owner Training | [7 empty] | 0% | 0% | 0% | 0%
Create datasphere | [7 empty] | 0% | 0% | 0% | 0%
Certificate of Occupancy | [7 empty] | 0% | 0% | 0% | 0%
Substantial Completion Certificate | [7 empty] | 0% | 0% | 0% | 0%
Schedule 11 month walk through | [7 empty] | 0% | 0% | 0% | 0%
Attic Stock Sign off | [7 empty] | 0% | 0% | 0% | 0%
Final T&B Report | [7 empty] | 0% | 0% | 0% | 0%
Final Commissioning Report | [7 empty] | 0% | 0% | 0% | 0%
179D Tax Credit | [7 empty] | 0% | 0% | 0% | 0%
Lessons Learned
[8 empty] | 0% | 0% | 0% | 0%
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event Specific Hourly Daily Weekly Bi Weekly Monthly Quarterly Annually
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Workflows are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## The "Company" Way
The Company Way | [10 empty] | Return to List of Ecosystems
Workstreams | Components Efficacy |  |  | As Is today Workstream Efficacy | Future Workstream Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
| People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Intangibles
Team Building | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Setting Cultural Expectations | Effective | Ineffective | Efficient | Effective | Exceptional
Company Culture | Efficient | Effective | Efficient | Efficient | Exceptional |  | 0% | 0% | 0% | 0%
Ownership of the Precon Process/Build Trust | Efficient | Efficient | Efficient | Efficient | Exceptional |  | 0% | 0% | 0% | 0%
Suspend Assumptions | Effective | Effective | Efficient | Effective | Exceptional |  | 0% | 0% | 0% | 0%
Best Idea Wins | Effective | Efficient | Efficient | Efficient | Exceptional |  | 0% | 0% | 0% | 0%
Ask "What does great look like?" | Effective | Efficient | Efficient | Efficient | Exceptional |  | 0% | 0% | 0% | 0%
Set clear expectations | Effective | Effective | Efficient | Effective | Exceptional |  | 0% | 0% | 0% | 0%
Celebrate stories | Effective | Ineffective | Efficient | Effective | Exceptional |  | 0% | 0% | 0% | 0%
Goal to give clients what they would want if they knew the possibilities. | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Demonstrate Leadership | [6 empty] | 0% | 0% | 0% | 0%
Demonstrate Responsiveness | [6 empty] | 0% | 0% | 0% | 0%
Demonstrate Relationship | [6 empty] | 0% | 0% | 0% | 0%
Demonstrate Awareness | [6 empty] | 0% | 0% | 0% | 0%
Demonstrate follow through | [6 empty] | 0% | 0% | 0% | 0%
Service over self - servant leadership | [6 empty] | 0% | 0% | 0% | 0%
Transparency | [6 empty] | 0% | 0% | 0% | 0%
Learning Organization | [6 empty] | 0% | 0% | 0% | 0%
Key Advantages
Help create spaces that promote healthy communities. | [6 empty] | 0% | 0% | 0% | 0%
How we treat each other | [6 empty] | 0% | 0% | 0% | 0%
Practicing Extreme Ownership Mindset | [6 empty] | 0% | 0% | 0% | 0%
[7 empty] | 0% | 0% | 0% | 0%
[7 empty] | 0% | 0% | 0% | 0%
[7 empty] | 0% | 0% | 0% | 0%
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work streams are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work streams are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.

## Risk Management
Risk Mangement | [10 empty] | Return to List of Ecosystems
Workstreams | Components Efficacy |  |  | As Is today Workstream Efficacy | Future Workstream Efficacy | Personnel Involved | Current Time % |  | Future Time % |  | Comments / Links | Owner | Action Required | Timing | Complete
| People | Process | Technology |  |  |  | Person 1 | Person 2 | Person 1 | Person 2
Contracts | [6 empty] | 0% | 0% | 0% | 0%
Owner | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Trade partners | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Purchase Orders | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Design Partner | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Change Orders | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Amendments | Efficient | Effective | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Insurance
Verifications | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
COI for All trade partners | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Builders Risk - who is carrying? | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Professional | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
General | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Auto | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Cyber | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Work Comp | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Manage Captive Insurance Requirements | Efficient | Ineffective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
P&P Bonds Trade Partners Greater than $500K | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Murray Issued P&P Bond | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Financial Risk | [6 empty] | 0% | 0% | 0% | 0%
Lien Waivers | Efficient | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Monitor AR | Efficient | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Positive Pay | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Fraud Protection | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Monthly Financial Reviews | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Cost Projections | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Accurate Estimating | Effective | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Safety Risk
Execute Safety Work Flow | Effective | Effective | Efficient | Effective | Exceptional |  | 0% | 0% | 0% | 0%
Safety Driven Culture | Effective | Effective | Efficient | Effective | Exceptional |  | 0% | 0% | 0% | 0%
Reputation Risk
Set and maintain owner expectations | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Follow through as promised | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
No surprises | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Extreme ownership mindset | Effective | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
Crisis Risk Mitigation
Maintain and train crisis procedures | Efficient | Efficient | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Be proactive to avoid | Efficient | Efficient | Efficient | Efficient | Exceptional |  | 0% | 0% | 0% | 0%
Employee Risk
Right person right seat | Efficient | Effective | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
HIring top level talent | Efficient | Effective | Efficient | Efficient | Efficient |  | 0% | 0% | 0% | 0%
Preemployment checks | Ineffective | Ineffective | Efficient | Ineffective | Efficient |  | 0% | 0% | 0% | 0%
Setting them up for success - Onboarding | Efficient | Effective | Efficient | Effective | Efficient |  | 0% | 0% | 0% | 0%
[7 empty] | 0% | 0% | 0% | 0%
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work streams are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work streams are the sum of people, processes, and technology components and is measured as follows: Ineffective - Does NOT produce desired expectation. Effective - Produces the desired expectation. Efficient - Consistently produces the desired expectation leveraging minimal resources. Exceptional - Consistently exceeds expectations with high quality and little to no waste.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: People are your most complicated asset and can make or break your business! It is imperative that you have the right people in the right position. Once there, leadership and or management must ensure the following: • They have a clear understanding of the vision, values, blueprint, and goals of the organization. They are provided expectations aligned with those goals that are explicitly defined, measured and adjusted as necessary. • They bring the following acumen to the organization: 1) Technical – Programmer, Carpenter, Analysist, 2) Behavioral – Professional, articulate, ability to follow through • They must be willing and capable to perform to the desired result. Note: If they are unwilling it doesn’t matter if they are capable! The right people in the right position begins with willingness! • Their acumen will be measured using the following criteria: Ineffective – They are unwilling or incapable to perform to the desired expectation. Effective – They are willing and capable to perform to the desired expectation. Efficient – They consistently perform to the desired expectation with minor assistance. Exceptional – They consistently exceed the desired expectation with optimal quality and little or no assistance.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Process component Processes should be intuitive and enable/assist people in meeting the blueprint and associated work streams of the organization. They must be defined, measured and adjusted as necessary. Ineffective - Processes change when people change. Quality is poor and waste is overly excessive. Effective - Processes stay the same regardless of the people. Quality is good but waste is still an issue. Efficient - Processes perform to the level of expectations. Quality is high and waste is minimal. Exceptional - Processes constantly exceeds expectations. Quality is exceptional and there is no waste.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technology component Technology should be intuitive and enable/assist people and processes! Must be defined, measured and adjusted as necessary. Ineffective - Constantly challenged with work around solutions and time latencies. Effective - Does the job but could do more … faster Efficient - Performs to the level of expectations. Exceptional - Consistently Exceeds Expectations and allows for expansion.